## Sheet1
Project Summary Costs
| Labor Total (Approximate) |  | 12357
| Furniture and Equipment |  | 40680
| Project Total (Approx) |  | 53037
Labor Costs
Hourly Rate
| Project Manager |  | 45
| Bob Adams |  | 35
| Jessica Thomas |  | 35
| Mary Ryan |  | 29
|  | Average | 36
Work Package |  | Time (hrs) | Hourly Rate | Approx Cost
Initiate Project
| Kickoff Meeting | 3 | 36 | 108
| Meeting with Management, team and stakeholders | 10.5 | 36 | 378
| Develop Project Charter & Scope proposal | 5 | 36 | 180
| Review and approval of project charter | 14 | 36 | 504
| Team Meeting for Project Plan | 3.5 | 36 | 126
Planning |  |  |  | 0
Requirements Gathering |  |  |  | 0
| Obtain input from Procurement Dept (FiberTel) on the preferred supplier and furniture | 3 | 36 | 108
| Obtain client input(FiberTel) on the PCs and other network hardware | 4.5 | 36 | 162
| Obtain Client input (FiberTel) on the transition assistance to MetroTech for Operation Support System | 4.5 | 36 | 162
| Obtain client input for Adirondack's assets transferred into the new Office space | 1.5 | 36 | 54
Assessment of Requirements |  |  |  | 0
| Determine Network Wiring Configuration | 6 | 36 | 216
| Verify Internet Access Systems Connectivity | 1.5 | 36 | 54
| Determine Furniture placement | 4.5 | 36 | 162
| Document specific networking requirements | 6 | 36 | 216
| Finalize design of new computer stations and Tables | 3 | 36 | 108
| Verify required software applications | 3 | 36 | 108
| Verify required network hardware and other peripheral equipment | 2.25 | 36 | 81
| Team Meeting for Procurement | 7 | 36 | 252
Procurement |  |  |  | 0
Procurement Order prep |  |  |  | 0
| Build list of required items | 2 | 36 | 72
| Obtain cost quotations from vendors | 8 | 36 | 288
| Refine and adjust project scope | 4 | 36 | 144
| Finalize Vendors for different products | 2 | 36 | 72
| Determine purchasing and financing procedures | 2 | 36 | 72
Place orders & Verify |  |  |  | 0
| Issue purchase orders for Hardware | 2 | 36 | 72
| Issue purchase orders for furniture | 3 | 36 | 108
| Verify correctness of hardware orders | 4 | 36 | 144
| Verify correctness of furniture orders | 4 | 36 | 144
| Procure Linux Server from MetroTech | 1 | 36 | 36
| Team Meeting for Execution | 7 | 36 | 252
Execution |  |  |  | 0
Assemble Furniture & Hardware |  |  |  | 0
| Place new furniture in Final Position | 16 | 36 | 576
| Assemble and verify operation of 10 new PC workstations | 20 | 36 | 720
| Assemble and verify operation of 10 new VOIP handsets | 7.5 | 36 | 270
| Assemble and test new scanner / printer | 9 | 36 | 324
Install & connect network hardware |  |  |  | 0
| Install Cisco ME 3400 switch | 1 | 36 | 36
| Connect system to local switch to core router | 1 | 36 | 36
| Install network cabling in buildings cells and walls | 24 | 36 | 864
| Connect networks outlets and confirm connectivity | 6 | 36 | 216
| Connect network patch cables | 2 | 36 | 72
| Install Linux server for MetroTech | 7.5 | 36 | 270
Configure & Install the assembled hardware & software |  |  |  | 0
| Configure and Test each individual PC workstation | 5.25 | 36 | 189
| Configure and Test each individual VoIP handset | 8.75 | 36 | 315
| Install and Test Copier/printer | 7 | 36 | 252
| Install and configure Wireless Access points | 7 | 36 | 252
| Install required software on New PCs | 17.5 | 36 | 630
| Cable Management | 2 | 36 | 72
| Team Meeting for Testing | 7 | 36 | 252
Testing |  |  |  | 0
| Verify operation of Wired Network | 6 | 36 | 216
| Verify operation of Wireless Network | 3 | 36 | 108
| Test copier/printer for network connectivity | 3 | 36 | 108
| Test the functioning of the Linux server for MetroTech | 4.5 | 36 | 162
| Test the operation of the Cisco ME 3400 switch | 6 | 36 | 216
| Verify correct placement of furniture | 2 | 36 | 72
| Test network connectivity with FiberTel internal network | 4.5 | 36 | 162
| Team meeting for project closeout | 3.5 | 36 | 126
Documentation and Training |  |  |  | 0
| Develop written diagrams and documentation | 40 | 36 | 1440
| Project close meeting with Management & client | 0.5 | 36 | 18
| Labor Total (Approximate) | 343.25 | 36 | 12357
| Labor Total (High) |  | 29 | 9954.25
| Labor Total (Low) |  | 45 | 15446.25
Hardware and Furniture Costs
|  | Number | Cost (each) | Total
| PC Workstations with monitors and Software suite | 10 | 1750 | 17500
| VoIP Handsets | 10 | 450 | 4500
| Patch Cables | 1 | 240 | 240
| Cubicle Furniture | 10 | 1275 | 12750
| Kyocera Network High speed copier/printer | 1 | 2950 | 2950
| Cisco Wireless Access Points | 2 | 160 | 320
| Cisco ME 3400 Switch | 1 | 1765 | 1765
| Wall Mount patch panel to be mounted at hub area | 1 | 150 | 150
| Network Wall Jacks | 1 | 240 | 240
| Network Cables | 1 | 265 | 265
|  |  | Equipment and Furniture Total | 40680
|  |  | Project Total | 53037